## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USGreatOutdoor:001 | 1 | Entity Class Design | RamTeja | 2020-08-03 | 5 hrs | 4 hrs | Completed | 3
|  | 2 | Table Design | RamTeja | 2020-08-03 | 4 hrs | 3 hrs | Completed | 4
|  | 3 | Application Architecture | Hemanth Reddy | 2020-08-03 | 3 hrs | 1 hrs | Completed | 2
|  | 4 | Use case diagram | Sunil | 2020-08-03 | 1 hrs | 0.5 hrs | Completed | 2
|  | 5 | Sequence Diagram | Kartikeya | 2020-08-03 | 5 hrs | 4 hrs | Completed | 3
|  | 6 | Each use case detail description | Chaitanya | 2020-08-03 | 6 hrs | 5 hrs | Completed | 6
|  | 7 | Class Layer diagram | sreeram | 2020-08-03 | 3 hrs | 2 hrs | Completed | 2
|  | 8 | Class Diagram | sai krishna | 2020-08-03 | 2 hrs | 1 hrs | Completed | 1.5
|  | 9 | Webservice URL Details | subham | 2020-08-03 | 3 hrs | 1 hrs | Completed | 2
2 | USGreatOutdoor:002 | 1 | Test plan for dao, | RamTeja | 2020-08-04 | 3 hrs | 2 hrs | Completed | 3
|  | 2 | Test plan for service | Hemanth Reddy | 2020-08-04 | 4 hrs | 3 hrs | Completed | 4
|  | 3 | Test plan for webservice methods | Subham | 2020-08-04 | 3 hrs | 1 hrs | Completed | 2
3 | USGreatOutdoor:003 | 1 | Creating a Spring boot starter project | Chaitanya | 2020-08-04 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Sreeram | 2020-08-04 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
|  | 3 | Adding server, jpa properties in application.properties | Sai krishna | 2020-08-04 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
4 | USGreatOutdoor:004 | 1 | Entity Class Design | RamTeja | 2020-08-04 | 3 hrs | 2 hrs | completed | 1.5 hrs
|  | 2 | Check tables are poulated in DB | Chaitanya | 2020-08-04 | 1 hrs | 1.5 hrs | complted | 45 min
|  | 3 | Populate the Data | Chaitanya | 2020-08-04 | 3o min | 1 hrs | complted | 30 min
5 | USGreatOutdoor:005 | 1 | Write a JPQL query to retrieve the product details for the given search, src in DAO layer | Hemanth Reddy | 2020-08-10 | 1 hrs | 45 min | complted | 45 min
|  | 2 | service method invoke the Dao and get the list of the product. If list is empty throw ProductNotFoundException "No Product Found" | sunil | 2020-08-10 | 1 hrs | 45 min | completed | 45 min
|  | 3 | Service method will check the item in inventeryand show wishlist or aad to cart option to the user | Subham | 2020-04-21 | 1 hr | 50 min | complted | 30 min
|  | 4 | REstController method get the details of the product and send to service to place order | Kartikeya | 2020-08-10 | 1 hr | 50 min | completed | 40 min
6 | USGreatOutdoor:006 | 1 | Write the JPQL query to get the product by product ID in DAO | Subham | 2020-08-10 | 1 hr | 50 min | complted | 45 min
|  | 2 | Write the JPQL query to get the User by User ID in DAO | Hemanth Reddy | 2020-08-10 | 1 hr | 45 min | complted | 40 min
|  | 3 | Write a code to insert placing order instance | Karthikeya | 2020-08-10 | 40 min | 30 min | complted | 25 min
|  | 4 | Service checks the product id and user id and the product is available or not | Subham | 2020-08-10 | 30 min | 25 min | Complted | 20 min
|  | 5 | If available deduts the item from the inventery | RamTeja | 2020-08-10 | 30 min | 30 min | Complted | 20 min
|  | 6 | generate the product ID and bind to added Product in the card | Subham | 2020-08-10 | 50 min | 45 min | Complted | 40 min
|  | 7 | RestController method get the details such as product ID, no of items, user ID and send to service method and returns card Id | Sunil | 2020-08-11 | 1 hr | 50 min | complted | 50 min
7 | USGreatOutdoor:007 | 1 | Showing Wishlist to user in this user story user can add Product to Wishlist and Remove From Wishlist. | Chaitanya | 2020-08-11 | 1 hr | 1 hrs | complted | 1 hr
8 | USGreatOutdoor:008 | 1 | AddressManagement in this user can add address,delete and update address before placing the order. | Hemanth Reddy | 2020-08-11 | 1.5 hrs | 1.5 hrs | complted | 1 hour20 min
9 | USGreatOutdoor:009 | 1 | Cancel Order in this user Story user can cancel order. | Sunil | 2020-08-11
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.