## Sheet1
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | Standard document | High | USGreatOutdoor:001 | Design Documentation for Backend application | Prabhu Ganesh | Sreeram | Average | Low | RD:1 Application SetUp | RD:Business Requirement Doc | Non-Functional | 22 hrs | Design is fullfilled agaist Business requirement
2 | Standard document |  | USGreatOutdoor:002 | Test Plan | Prabhu Ganesh | Chaitanya Kumar | Average | Low | RD:2 Test plan | RD:Business Requirement Doc | Non-Functional | 8 hrs | Check the test case is fullfiled with user accepance criteria document
3 | Standard document | High | USGreatOutdoor:003 | Bootstrapping the project | Prabhu Ganesh | Sunil | Simple | Low | RD:3 Bootstraping | RD: GreatoutdoorDocumen_ver1 | Non-Functional | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
4 | Work session | High | USGreatOutdoor:004 | Entity Class and TableDEsign and Populating the data | Prabhu Ganesh | Sai krishna | Complex | Low | RD4: Entity Class Design and RD3: Table Design | RD: GreatoutdoorDocument_ver2 | Functional | 8 hrs | Checking against the Table design in RD
5 | Work session | High | USGreatOutdoor:005 | Displaying product detail and other product related for the given search | Prabhu Ganesh | Shubham Rao | Average | Low | RD 5: Displaying the products | RD: GreatoutdoorDocument_ver3 | Functional | 16 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
6 | Work session | High | USGreatOutdoor:006 | Adding the selected item to the cart | Prabhu Ganesh | Ram Teja reddy | Complex | Low | RD6: Adding items to cart | RD: GreatoutdoorDocument_ver4 | Functional | 7 hrs | TC_Service_02,TC_DAO_02, TC_UI_03
7 | Work session | High | USGreatOutdoor:007 | Showing wishlist to the user | Prabhu Ganesh | Chaitanya Kumar | Average | Low | RD7:Showing wishlist | RD: GreatoutdoorDocument_ver5 | Functional | 5 hrs | TC_Service_02,TC_DAO_02, TC_UI_04
8 | Work session | High | USGreatOutdoor:008 | Address Management by user | Prabhu Ganesh | Hemanth Kumar | Complex | High | RD:Add ,Delete and update Address by user | RD: GreatoutdoorDocument_ver6 | Functional | 16 hrs | TC_Service_02,TC_DAO_02, TC_UI_05
9 | Work session | High | USGreatOutdoor:009 | Cancel Product by user | Prabhu Ganesh | Karthikeya | Average | Average | RD9: Cancel Product | RD: GreatoutdoorDocument_ver7
Note on B2: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C2: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D2: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E2: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F2: Brief description of the requirements necessary to fulfill the objective
Note on G2: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H2: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I2: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J2: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K2: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L2: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M2: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N2: Description of the condition(s) that indicate the requirement has been satisfied.
Note on O2: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on P2: This column is used to provide supporting information, such as changes to the original requirement.