## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USGreatOutdoor:001 | 1 | Entity Class Design | RamTeja | 2020-08-03 | 5 hrs | 4 hrs | Completed | 3
|  | 2 | Table Design | RamTeja | 2020-08-03 | 4 hrs | 3 hrs | Completed | 4
|  | 3 | Application Architecture | Hemanth Reddy | 2020-08-03 | 3 hrs | 1 hrs | Completed | 2
|  | 4 | Use case diagram | Sunil | 2020-08-03 | 1 hrs | 0.5 hrs | Completed | 1
|  | 5 | Sequence Diagram | Kartikeya | 2020-08-03 | 5 hrs | 4 hrs | Completed | 3
|  | 6 | Each use case detail description | Chaitanya | 2020-08-03 | 6 hrs | 5 hrs | Completed | 6
|  | 7 | Class Layer diagram | sreeram | 2020-08-03 | 3 hrs | 2 hrs | Completed | 2
|  | 8 | Class Diagram | sai krishna | 2020-08-03 | 2 hrs | 1 hrs | Completed | 1.5
|  | 9 | Webservice URL Details | subham | 2020-08-03 | 3 hrs | 1 hrs | Completed | 2
2 | USGreatOutdoor:002 | 1 | Test plan for dao, | RamTeja | 2020-08-04 | 3 hrs | 2 hrs | Completed | 3
|  | 2 | Test plan for service | Hemanth Reddy | 2020-08-04 | 4 hrs | 3 hrs | Completed | 4
|  | 3 | Test plan for webservice methods | Subham | 2020-08-04 | 3 hrs | 1 hrs | Completed | 2
3 | USGreatOutdoor:003 | 1 | Creating a Spring boot starter project | Chaitanya | 2020-08-04 | 2 hrs | 0.5 hrs | Completed | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Sreeram | 2020-08-04 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
|  | 3 | Adding server, jpa properties in application.properties | Sai krishna | 2020-08-04 | 1 hrs | 0.5 hrs | Completed | 0.5 hrs
4 | USGreatOutdoor:004 | 1 | Entity Class Design | RamTeja | 2020-08-04 | 3 hrs | 2 hrs | completed | 1.5 hrs
|  | 2 | Check tables are poulated in DB | Chaitanya | 2020-08-04 | 1 hrs | 1.5 hrs | complted | 45 min
|  | 3 | Populate the Data | Chaitanya | 2020-08-04 | 3o min | 1 hrs | complted | 30 min
5 | USGreatOutdoor:005 | 1 | Write a JPQL query to retrieve the product details for the given search, src in DAO layer | Hemanth Reddy | 2020-08-10 | 1 hrs | 45 min | complted | 45 min
|  | 2 | service method invoke the Dao and get the list of the product. If list is empty throw ProductNotFoundException "No Product Found" | sunil | 2020-08-10 | 1 hrs | 45 min | completed | 45 min
|  | 3 | Service method will check the item in inventeryand show wishlist or aad to cart option to the user | Subham | 2020-04-21 | 1 hr | 50 min | complted | 30 min
|  | 4 | REstController method get the details of the product and send to service to place order | Kartikeya | 2020-08-10 | 1 hr | 50 min | completed | 40 min
6 | USGreatOutdoor:006 | 1 | Write the JPQL query to get the product by product ID in DAO | Subham | 2020-08-10 | 1 hr | 50 min | complted | 45 min
|  | 2 | Write the JPQL query to get the User by User ID in DAO | Hemanth Reddy | 2020-08-10 | 1 hr | 45 min | complted | 40 min
|  | 3 | Write a code to insert placing order instance | Karthikeya | 2020-08-10 | 40 min | 30 min | complted | 25 min
|  | 4 | Service checks the product id and user id and the product is available or not | Subham | 2020-08-10 | 30 min | 25 min | Complted | 20 min
|  | 5 | If available deduts the item from the inventery | RamTeja | 2020-08-10 | 30 min | 30 min | Complted | 20 min
|  | 6 | generate the product ID and bind to added Product in the card | Subham | 2020-08-10 | 50 min | 45 min | Complted | 40 min
|  | 7 | RestController method get the details such as product ID, no of items, user ID and send to service method and returns card Id | Sunil | 2020-08-11 | 1 hr | 50 min | complted | 50 min
7 | USGreatOutdoor:007 | 1 | Showing Wishlist to user in this user story user can add Product to Wishlist and Remove From Wishlist. | Chaitanya | 2020-08-11 | 1 hr | 1 hrs | complted | 1 hr
8 | USGreatOutdoor:008 | 1 | AddressManagement in this user can add address,delete and update address before placing the order. | Hemanth Reddy | 2020-08-11 | 1.5 hrs | 1.5 hrs | complted | 1 hour20 min
9 | USGreatOutdoor:009 | 1 | Cancel Order in this user Story user can cancel order. | Sunil | 2020-08-11
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.