## Greater outdoors
| Main User Story | SubTask | Name
1 | WishList | Add to Wishlist(retailer/Representative)
View Wishlist
| Add and place order | add to cart | D. Rama Teja Reddy
remove from cart
update quantity
| User Management | User Registration | J. Sai Krishna
User Login
User Logout
| Address management | add Address | Hemanth Reddy chityala
delete Address
update Address
view all address
| Product Management | add product | Shubham Rao
delete product
edit product
search product
filter product
| Shelf time Report | Yearly Shelf Report | Siva sreeram
Monthly Shelf Report
Quaterly Shelf Report
| making payment | making payment for product | sunil kumar
making payment for order
| cancel management | cancelling the order before dispatch
|  | cancelling the product before order dispatch | karthik

## Ramteja
Task No | Task Name | Estimated Time | Actual Time | Alloted on day | Comments
1 | Add to cart
1.1 | Entity,Service | 3 |  | 2020-08-04
1.2 | DAO | 2 |  | 2020-08-04
1.3 | Dto,exceptions | 1.5 |  | 2020-08-04
2 | Update the avaliable stock
2.1 | Entity,Service | 2 |  | 2020-08-04
2.2 | DAO | 2.5 |  | 2020-08-10
2.3 | Dto,exceptions | 1 |  | 2020-08-10
3 | Remove from cart
3.1 | Entity,Service | 1.5 |  | 2020-08-10
3.2 | DAO | 2 |  | 2020-08-10
3.3 | Dto,exceptions | 1 |  | 2020-08-11
4 | Place the order
4.1 | Entity,Service | 2.5 |  | 2020-08-11
4.2 | DAO | 2 |  | 2020-08-11
4.3 | Dto,exceptions | 1.5 |  | 2020-08-11

## Chaitanya
Task No. | Task Name | Estimated hours/Time | Actual Time taken | Alloted on day | Comments
1 | WishList
1.1 | Add to WishList
1.1.1 | Entity | 2 | 2 | 2020-08-04
1.1.2 | Dao DTO | 1.5 | 2 | 2020-08-04
1.1.3 | Exception | 1 | 1 | 2020-08-10
1.1.4 | Service | 2.5 | 3 | 2020-08-11
1.2 | View Wishlist
1.1.1 | Entity | 2 | 3 | 2020-08-04
1.1.2 | Dao DTO | 1.5 | 1 | 2020-08-04
1.1.3 | Exception | 1 | 1 | 2020-08-10
1.1.4 | Service | 2.5 | 3 | 2020-08-11
1.3 | Remove Product from wishlist
1.3.1 | Entity | 2 | 3 | 2020-08-04
| Dao DTO | 1 | 2 | 2020-08-04
| Exception | 1 | 1 | 2020-08-10
| Service | 1 | 1 | 2020-08-11

## sai Krishna
Task No. | Task Name | Estimated Hours/Time | Actual Time Taken | Alloted on Day | Comments
1 | User Management System
1.1 | User Registration
1.1.1 | Entity,Service | 3 |  | 2020-08-04
1.1.2 | DAO | 2 |  | 2020-08-04
1.1.3 | Dto,Exceptions | 1.5 |  | 2020-08-04
1.2 | User Login
1.2.1 | Entity,Service | 2 |  | 2020-08-04
1.2.2 | DAO | 2.5 |  | 2020-08-10
1.2.3 | Dto,exceptions | 1 |  | 2020-08-10
1.3 | User Logout
1.3.1 | Entity,Service | 2 |  | 2020-08-11
1.3.2 | DAO | 2.5 |  | 2020-08-11
1.3.3 | Dto,exceptions | 1 |  | 2020-08-11

## subham
Task no. | Task Name | Estimated hours/Time | Actual Time taken | Alloted on day | Status | Comments
1 | Product Management
Test Plan
| Test Plan for DAO | 2 |  | Tuesday(5)
| Test Plan for Service | 2 |  | Tuesday(5)
1.1 | Add Product
1.1.1 | create entities | 3 |  | Tuesday(5)
1.1.2 | Dao and service layers | 5 |  | Tuesday(5)
1.1.3 | Exception Handling | 2 |  | Tuesday(11)
1.2 | Delete Product
1.2.1 | Dao and service layers | 3 |  | Monday(10)
1.2.2 | Exception Handling | 2 |  | Tuesday(11)
1.3 | Edit Product
1.3.1 | Dao and service layers | 3 |  | Monday(10)
1.3.2 | Exception Handling | 2 |  | Tuesday(11)
1.4 | Search Product
1.4.1 | Dao and service layers | 2 |  | Monday(10)
1.4.2 | Exception Handling | 2 |  | Tuesday(11)
1.5 | Filter Product
1.5.1 | Dao and Service layers | 3 |  | Monday(10)
1.5.2 | Exception Handling | 3 |  | Tuesday(11)
1.6 | Add Product Master
1.6.1 | Dao and Service layers | 2 |  | Monday(10)
1.6.2 | Excpetion Handling | 2 |  | Tuesday(11)

## Hemanth
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Addresses
| Test cases | 2 |  | Tuesday(4)
1.1 | Add Address
1.1.1 | create entities | 5 |  | Tuesday(4
1.1.2 | Dao and service layers | 2+1 |  | Tuesday(4,11)
1.1.3 | Exception Handling | 1 |  | Tuesday(11)
1.2 | Delete Address
1.2.1 | Dao and service layers | 3 |  | Monday(10)
1.2.2 | Exception Handling | 1 |  | Tuesday(11)
1.3 | Update Address
1.3.1 | Dao and service layers | 3 |  | Monday(10)
1.3.2 | Exception Handling | 1 |  | Tuesday(11)
1.4 | Show All Addresses
1.4.1 | Dao and service layers | 4 |  | Monday(11)
1.4.2 | Exception Handling | 1 |  | Tuesday(11)

## sunil
Task no | Task Name | Estimated hours/Time | Actual Time taken | Alloted on day | Comments
1 | payment management
| Test plan for DAO | 2 |  | Tuesday(4)
| Test plan for Service | 3 |  | Tuesday(4)
1.1 | making payment for product
1.1.1 | Dao and Service layers | 5 |  | Tuesday(4)
1.1.2 | Exception Handling | 2 |  | Monday(10)
1.2 | making payment for order
1.2.1 | Dao and Service layers | 4 |  | Monday(10)
1.2.2 | Exception Handling | 3 |  | Tuesday(11)

## Karthikeya
Task no. | Task Name | Estimated hours/Time | Actual Time taken | Alloted on day | Comments
1 | Cancel Management
Test Plan
| Test Plan for DAO | 2 |  | Tuesday(5)
| Test Plan for Service | 2 |  | Tuesday(5)
1.1 | Cancel order
1.1.1 | Dao and service layers | 5 |  | Tuesday(5)
1.1.2 | Exception Handling | 2 |  | Monday
1.2 | Cancel product
1.2.1 | Dao and service layers | 3 |  | Monday(10)
1.2.2 | Exception Handling | 2 |  | Tuesday(11)

## sreeram
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Shelf Time report
1.1 | Received Time Stamp
1.1.1 | Entity | 0.5 |  | 2020-08-04
1.1.2 | Dao DTO | 1 |  | 2020-08-04
1.1.3 | Exception | 0.5 |  | 2020-08-10
1.1.4 | Service | 1 |  | 2020-08-11
1.2 | Sold Time Stamp
1.2.1 | Entity | 0.5 |  | 2020-08-04
1.2.2 | Dao DTO | 1 |  | 2020-08-04
1.2.3 | Exception | 0.5 |  | 2020-08-10
1.2.4 | Service | 1 |  | 2020-08-11
1.3 | Yearly Shelf Report
1.3.1 | Exception | 1 |  | 2020-08-10
1.3.2 | Service | 1.5 |  | 2020-08-11
1.4 | Quaterly Shelf Report
1.4.1 | Exception | 1 |  | 2020-08-10
1.4.2 | Service | 1.5 |  | 2020-08-11
1.5 | Monthly Shelf Report
1.5.1 | Exception | 1 |  | 2020-08-10
1.5.2 | Service | 1.5 |  | 2020-08-11